PLANNING COMMISSION

REGULAR MEETING

April 8, 2015

ATT: Brad Lackey, Phil Edelstein, Peter Barus, Zoning Administrator Gig Zboray and John Bennett of WRC.

Meeting called to order at 6:40 PM.

Addition/Changes to Agenda: Add “approve Minutes of March 11, 2015 meeting”

Brad questioned John about who is the Grant Administrator of the Municipal Planning Grant since it was not included in our grant award.  John will ask the WRC if they will do it (either gratis or at a cost of up to $600).  It was agreed that it makes more sense for the WRC to administer the grant themselves then to answer all the questions we would have if we were to do it.

Peter made motion to approve the Minutes with of March 11, 2015, 2nd by Brad.  All in favor.

IMPORTANT  The Town Plan must be updated and adopted by August 3, 2015.  We will not have time to update all aspects of the plan at this time.  After the plan is adopted a full revision will be completed and adopted.  The time-frame to meet this deadline is as follows:

April 13, 2015 ALL updates must be submitted to John

April 20, 2015 John will email the final draft

April 22, 2015 Planning Commission adopts the updated Plan at a special meeting

May – Town Plan draft mailed out to abutting towns

June – Planning Commission holds hearing on Town Plan

July – Selectboard holds hearing on Town Plan

August – final adoption

September – continue work on a complete update

Review of Town Plan changes made to date:

Phil will write up brief descriptions for the history pages (2011-2014)on Page 4 and do some wording changes on Page 6.

Housing, page 7 – minor changes that John added for now.  Thorough review and update later.

Figure 5, page 9 – John is trying to get help on this from others at WRC.  This figure (and the paragraph that follows) can be deleted temporarily and updated later.

Figure 6, page 10 – OK to leave as is for now, update later.  Remove the paragraph below.

Table 6, page 11 – Remove Table 6 and replace with Median Household Income (call it Figure 7) and include John’s sentence (currently in red).

Page 12 – Median Household Income Comparison will become “Figure 8”.

All figures and tables need to be numbered correctly.

Page 13 – minor changes that John already made are OK.

Pages 13-14 Public Safety OK as updated, Waste Water Disposal OK as updated (remove last paragraph in bold print), Electric Distribution OK as updated.  Solid Waste Disposal, remove paragraph that starts “a number of residents hire…” – Gig will read over one more time.

Library – page 15 Kristen to update this.

Health & Emergency Services, page 16 Gig will look at the Social Services paragraph.

Communications, page 16 – Phil to update this section.

Education, page 17 – Linda to work with principal on this section.

Child Care, page 18 – 3rd paragraph delete last sentence then add to 2nd paragraph.  Delete everything after.

Historic Resources, page 19 minor changes – OK.

Public Recreation, page 20 Gig will read over again.

Scenic Resources, page 21 Gig will compare to the changes we originally made.

ADD:  Fluvial Erosion – to Water Resources section after Floodplains.  We will use a version of the Wardsboro example.

Villages Linda this is critical, you said in the past you would work on this, if you don’t know what it is, please ask John.

All updates that are needed are indicated in RED.  These need to be to John by MONDAY, APRIL 13th!

Next meeting is a Special Meeting on Wednesday, April 22, 2015 at 6:30pm.  It is important to a quorum to vote to adopt the Plan.  Brad will be absent.

Meeting adjourned at 8:31pm